## SCHEDULE
SCHEDULE
DATE | Agenda | Jana | Johanna | Renzo
2022-06-01 | Meeting with client | Jana | Johanna | Renzo
2023-06-01 | PJR w1 | Jana | Johanna | Renzo
2024-06-01 | PJR w2 | Jana | Johanna | Renzo
| Event Table (propose) Stud | Jana | Johanna | Renzo
2025-06-01 | Event Table (propose) Ad |  | Johanna
| Use Case FD (Propose) Stud & Ad |  | Johanna
| Event Table (existing) Ad |  |  | Renzo
2026-06-01 | Event table (Existing) Stud | Jana
| Use Case Diagram (Existing) | Jana
| 2. Event table (existing - admin) |  |  | Renzo
| 2. UseCaseFD (propose - Stud & Ad) |  | Johanna
| Use Case Diagram (Propose) Stud & Ad | Jana
2027-06-01 | Wiki (Objective, Description) |  | Johanna
2016-06-29 | Activity Diagram |  | Johanna
| Class Diagram |  |  | Renzo
2016-06-30 | Object Diagram | Jana | Johanna | Renzo
| State Diagram | Jana | Johanna | Renzo
| Timing Diagram | Jana | Johanna | Renzo
| Consultation With Sir Sean/Sir Quesada | Jana | Johanna | Renzo
| PSR w3 | Jana | Johanna | Renzo
| Wiki (Scope and Limitation) |  | Johanna
2001-07-01 | Wiki |  | Johanna
| Event table (Existing) Stud & Ad | Jana | Johanna | Renzo
| 2. UML Diagrams (Class, communication, timing) |  | Johanna | Renzo
| Use Case Diagram (Existing) Stud & Ad | Jana
| 2. PSR w3 | Jana
2016-07-02 | 2. Communication |  |  | Renzo
2016-07-03 | 2. State Machine | Jana
| Wiki |  | Johanna
| 2. Object Diagram | Jana
| Package Diagram |  |  | Renzo
| Sample GUI |  | Johanna
| 2. Class Diagram |  |  | Renzo
2005-07-01 | 3. Communication Diagram |  |  | Renzo
| 3. Timing Diagram |  | Johanna
| Sample GUI |  | Johanna
| 3. Package Diagram |  |  | Renzo
2006-07-01 | Component Diagram |  | Johanna
| Wiki | Jana | Johanna | Renzo
| Package Diagram |  |  | Renzo
| Deployment Diagram | Jana
| Timing Diagram |  | Johanna
2007-07-01 | Consultation With Sir Sean/Sir Quesada | Jana | Johanna | Renzo
| Use Case FD Existing | Jana
| Event table existing | Jana
| wiki | Jana | Johanna
| update event table (propose) |  | Johanna
| Draft for deployment diagram | Jana
| Draft for class diagram |  |  | Renzo
2008-07-01 | ERD |  | Johanna
| Component Diagram |  | Johanna
| Use Case FD (Propose) Stud & Ad |  | Johanna
| Activity Diagram |  | Johanna
| Object Diagram | Jana
| Class Diagram |  |  | Renzo
| Communication |  |  | Renzo
2010-07-01 | Deployment Diagram | Jana
| Timing Diagram |  | Johanna
| State Diagram | Jana
| Composite Diagram |  |  | Renzo
| Use Case FD (Propose) Stud & Ad |  | Johanna